## Sheet1
Planning
(planning na de concept fase)
Naam | 2017-05-08 | 2017-05-14 | 2017-05-15 | 2017-05-21 |  |  | 2017-05-22 | 2017-05-28 | 2017-05-29 | 2017-05-04 | 2017-06-05 | 2017-06-11 | 2017-06-12 | 2017-06-18 | 2017-06-19 | 2017-06-28 | 2017-06-29 | 2017-06-30 | 2017-06-30 | presentatie
David | Crafting |  | Slab |  |  |  | Minotaur Scripts |  | Minotaur
| Slab |  | Quest Implementing |  |  |  | Bunny Script
| Pickup Script |  | Remake Quest HUD
Crafting Implementing
Walter | Water Shader |  | Combat Script |  |  |  | Arms Animations Implementing
PlayerController
PlayerController 2.0
DialogueManager
Rilana | Lady-3D |  | Minotaur Finishing |  | Minotaur Rig |  | Bed
| Lady-U4 |  | Alchemist-3D |  | Alchemist Rig |  | Chair
|  |  | Alchemist-4U |  | Lady Rig |  | Table
Alchemist-2D
Janneke | House Textures |  | Flowers |  | Sprites |  | Pots
|  |  | Bunny |  | UISlab | priority | Pans
|  |  | Bushes |  |  |  | Candle
Mushroom
Shields Textures
Gerwin | Lvl Design |  | Temple Maze Implementing
| Vegetation |  | Vegetation
Thomas | new in group (NIG) |  | Arms Animations
Arne | new in group (NIG)
Dees | new in group (NIG)

## Sheet2
Assetlist
2D | Textures |  | 6A | Animaties |  | TXT | Textures | INT | Interactives
3D | Model |  | 7S | Sound |  | ENV | Environment | SPR | Sprites
4U | Unwrap |  | 8P | Particle |  | PRP | Prop
5R | Rigging |  | 9Sc | Script |  | Char | Character
Object |  | Code |  |  | Priority | Member
Characters
Minotaurus (Boss) |  | 2D-Char-Minotaurus |  |  | A | Rilana
|  | 3D-Char-Minotaurus |  |  | A | Rilana
|  | 4U-Char-Minotaurus |  |  | A | Rilana
|  | 5R-Char-Minotaurus |  |  | A | Rilana
Theseus |  | 2D-Char-Theseus |  |  | A | Rilana
|  | 3D-Char-Theseus |  |  | A | Rilana
|  | 4U-Char-Thesues |  |  | A | Rilana
|  | 5R-Char-Theseus |  |  | A | Rilana
Lady |  | 2D-Char-Lady |  |  | A | Maaike
|  | 3D-Char-Lady |  |  | A | Maaike
|  | 4U-Char-Lady |  |  | A | Maaike
|  | 5R-Char-Lady |  |  | A | Maaike
Alchemist |  | 2D-Char-Alchemist |  |  | B
|  | 3D-Char-Alchemist |  |  | B
|  | 4U-Char-Alchemist |  |  | B
|  | 5R-Char-Alchemist |  |  | B
Environment
Houses
DoorWall |  | 2D-ENV-Doorwall |  |  | A
|  | 3D-ENV-Doorwall |  |  | A
|  | 4U-ENV-Doorwall |  |  | A
Window wall |  | 2D-ENV-Winwall |  |  | A
|  | 3D-ENV-Winwall |  |  | A
|  | 4U-ENV-Winwall |  |  | A
Wall |  | 2D-ENV-Wall |  |  | A
|  | 3D-ENV-Wall |  |  | A
|  | 4U-ENV-Wall |  |  | A
Window wall 2 |  | 2D-ENV-Winwall2 |  |  | B
|  | 3D-ENV-Winwall2 |  |  | B
|  | 4U-ENV-Winwall2 |  |  | B
Stair piece |  | 2D-ENV-Stair |  |  | A
|  | 3D-ENV-Stair |  |  | A
|  | 4U-ENV-Stair |  |  | A
Floor piece |  | 2D-ENV-Floor |  |  | A
|  | 3D-ENV-Floor |  |  | A
|  | 4U-ENV-Floor |  |  | A
Roof piece 1 |  | 2D-ENV-Roof1 |  |  | A
|  | 3D-ENV-Roof1 |  |  | A
|  | 4U-ENV-Roof1 |  |  | A
Roof piece 2 |  | 2D-ENV-Roof2 |  |  | B
|  | 3D-ENV-Roof2 |  |  | B
|  | 4U-ENV-Roof2 |  |  | B
Roof Terrace |  | 2D-ENV-RoofTer |  |  | A
|  | 3D-ENV-RoofTer |  |  | A
|  | 4U-ENV-RoofTer |  |  | A
Wall Edge |  | 2D-ENV-WallEdge |  |  | A
|  | 3D-ENV-WallEdge |  |  | A
|  | 4U-ENV-WallEdge |  |  | A
Temple
Pillar |  | 2D-ENV-TemplePillar |  |  | A
|  | 3D-ENV-TemplePillar |  |  | A
|  | 4U-ENV-TemplePillar |  |  | A
Wall |  | 2D-ENV-TempleWall |  |  | A
|  | 3D-ENV-TempleWall |  |  | A
|  | 4U-ENV-TempleWall |  |  | A
Roof |  | 2D-ENV-TempleRoof |  |  | A
|  | 3D-ENV-TempleRoof |  |  | A
|  | 4U-ENV-TempleRoof |  |  | A
Floor |  | 2D-ENV-TempleFloor |  |  | A
|  | 3D-ENV-TempleFloor |  |  | A
|  | 4U-ENV-TempleFloor |  |  | A
Stairs |  | 2D-ENV-TempleStair |  |  | A
|  | 3D-ENV-TempleStair |  |  | A
|  | 4U-ENV-TempleStair |  |  | A
Labyrinth piece 1 |  | 2D-ENV-Labyrinth1 |  |  | A
|  | 3D-ENV-Labyrinth1 |  |  | A
|  | 4U-ENV-Labyrinth1 |  |  | A
Labyrinth piece 2 |  | 2D-ENV-Labyrinth2 |  |  | B
|  | 3D-ENV-Labyrinth2 |  |  | B
|  | 4U-ENV-Labyrinth2 |  |  | B
Labyrinth circle |  | 2D-ENV-LabyCircle |  |  | A
|  | 3D-ENV-LabyCircle |  |  | A
|  | 4U-ENV-LabyCircle |  |  | A
Labyrinth piller |  | 2D-ENV-LabyPillar |  |  | A
|  | 3D-ENV-LabyPillar |  |  | A
|  | 4U-ENV-LabyPillar |  |  | A
Nature
Flower 1 |  | 2D-ENV-Flower1 |  |  | A
|  | 3D-ENV-Flower1 |  |  | A
|  | 4U-ENV-Flower1 |  |  | A
Flower 2 |  | 2D-ENV-Flower2 |  |  | B
|  | 3D-ENV-Flower2 |  |  | B
|  | 4U-ENV-Flower2 |  |  | B
Flower 3 |  | 2D-ENV-Flower3 |  |  | B
|  | 3D-ENV-Flower3 |  |  | B
|  | 4U-ENV-Flower3 |  |  | B
Tree 1 |  | 2D-ENV-Tree1 |  |  | A
|  | 3D-ENV-Tree1 |  |  | A
|  | 4U-ENV-Tree1 |  |  | A
Tree 2 |  | 2D-ENV-Tree2 |  |  | B
|  | 3D-ENV-Tree2 |  |  | B
|  | 4U-ENV-Tree2 |  |  | B
Mushroom 1 |  | 2D-ENV-Mushroom1 |  |  | A
|  | 3D-ENV-Mushroom1 |  |  | A
|  | 4U-ENV-Mushroom1 |  |  | A
Mushroom 2 |  | 2D-ENV-Mushroom2 |  |  | B
|  | 3D-ENV-Mushroom2 |  |  | B
|  | 4U-ENV-Mushroom2 |  |  | B
Bush 1 |  | 2D-ENV-Bush1 |  |  | A
|  | 3D-ENV-Bush1 |  |  | A
|  | 4U-ENV-Bush1 |  |  | A
Bush 2 |  | 2D-ENV-Bush2 |  |  | B
|  | 3D-ENV-Bush2 |  |  | B
|  | 4U-ENV-Bush2 |  |  | B
Bunny |  | 2D-ENV-Bunny |  |  | A
|  | 3D-ENV-Bunny |  |  | A
|  | 4U-ENV-Bunny |  |  | A
|  | 5R-ENV-Bunny |  |  | A
Rocks |  | 2D-ENV-Rocks |  |  | A
|  | 3D-ENV-Rocks |  |  | A
|  | 4U-ENV-Rocks |  |  | A
Treetrunks |  | 2D-ENV-Treetrunks |  |  | A
|  | 3D-ENV-Treetrunks |  |  | A
|  | 4U-ENV-Treetrunks |  |  | A
Props
Items
Sword |  | 2D-PRP-Sword |  |  | A | Janneke
|  | 3D-PRP-Sword |  |  | A | Janneke
|  | 4U-PRP-Sword |  |  | A | Janneke
Axe |  | 2D-PRP-Axe |  |  | A | Rilana
|  | 3D-PRP-Axe |  |  | A | Rilana
|  | 4U-PRP-Axe |  |  | A | Rilana
Torch |  | 2D-PRP-Torch |  |  | A
|  | 3D-PRP-Torch |  |  | A
|  | 4U-PRP-Torch |  |  | A
Props
Flower Box |  | 2D-PRP-Flowerbox |  |  | A
|  | 3D-PRP-Flowerbox |  |  | A
|  | 4U-PRP-Flowerbox |  |  | A
Chair |  | 2D-PRP-Chair |  |  | A
|  | 3D-PRP-Chair |  |  | A
|  | 4U-PRP-Chair |  |  | A
Table |  | 2D-PRP-Table |  |  | A
|  | 3D-PRP-Table |  |  | A
|  | 4U-PRP-Table |  |  | A
Candle |  | 2D-PRP-Candle |  |  | A
|  | 3D-PRP-Candle |  |  | A
|  | 4U-PRP-Candle |  |  | A
Pillars |  | 2D-PRP-Pillars |  |  | A
|  | 3D-PRP-Pillars |  |  | A
|  | 4U-PRP-Pillars |  |  | A
Well |  | 2D-PRP-Well |  |  | A
|  | 3D-PRP-Well |  |  | A
|  | 4U-PRP-Well |  |  | A
Chest |  | 2D-PRP-Chest |  |  | A
|  | 3D-PRP-Chest |  |  | A
|  | 4U-PRP-Chest |  |  | A
Bones |  | 2D-PRP-Bones |  |  | A
|  | 3D-PRP-Bones |  |  | A
|  | 4U-PRP-Bones |  |  | A
Shields |  | 2D-PRP-Shields |  |  | A
|  | 3D-PRP-Shields |  |  | A
|  | 4U-PRP-Shields |  |  | A
Jars |  | 2D-PRP-Jars |  |  | A
|  | 3D-PRP-Jars |  |  | A
|  | 4U-PRP-Jars |  |  | A
Hanging Torch |  | 2D-PRP-HangTorch |  |  | A
|  | 3D-PRP-HangTorch |  |  | A
|  | 4U-PRP-HangTorch |  |  | A
Coins |  | 2D-PRP-Coins |  |  | B
|  | 3D-PRP-Coins |  |  | B
|  | 4U-PRP-Coins |  |  | B
Scrolls |  | 2D-PRP-Scroll |  |  | B
|  | 3D-PRP-Scroll |  |  | B
|  | 4U-PRP-Scroll |  |  | B
Bed |  | 2D-PRP-Bed |  |  | A
|  | 3D-PRP-Bed |  |  | A
|  | 4U-PRP-Bed |  |  | A
Pots |  | 2D-PRP-Pots |  |  | A
|  | 3D-PRP-Pots |  |  | A
|  | 4U-PRP-Pots |  |  | A
couch |  | 2D-PRP-Couch |  |  | A
|  | 3D-PRP-Couch |  |  | A
|  | 4U-PRP-Couch |  |  | A
Code
CraftingStation |  | 9Sc-CraftingStation |  |  | A
GameManager |  | 9Sc-GameManager |  |  | A
Minotaur |  | 9Sc-Minotaur |  |  | A
Npc |  | 9Sc-Npc |  |  | A
DialogueManager |  | 9Sc-DialogueManager |  |  | A
InventoryManager |  | 9Sc-InventoryManager |  |  | A
Item |  | 9Sc-Item |  |  | A
FpsInputController |  | 9sc-FpsInputController |  |  | A
CombatManager |  | 9sc-CombatManager |  |  | A
UIManager |  | 9Sc-UIManager |  |  | A
Particle/Sprite
Grass |  | 2D-ENV-Grass |  |  | A
Cloud |  | 8P-ENV-Cloud |  |  | A
Waterfall |  | 8P-eNV-Waterfall |  |  | A
tempel
building
props
axe
tablet