## Sheet1
Planning
(planning na de concept fase)
Naam | 2017-05-08 | 2017-05-14 |  | 2017-05-15 | 2017-05-21 |  |  | 2017-05-22 | 2017-05-28 | 2017-05-29 | 2017-05-04 | 2017-06-05 | 2017-06-11 | 2017-06-12 | 2017-06-18 | 2017-06-19 | 2017-06-28 | 2017-06-29 | 2017-06-30 | 2017-06-30 | presentatie
David | crafting |  |  | slab |  |  |  | minotaur scripts |  | minotaur
| slab |  |  | quest implementing |  |  |  | `bunny script
| pickup script |  |  | remake quest hud
crafting implementing
Walter | player controller |  | arm animations | combat scripts
| dialogue |  | water prefab | player controller 2.0
pauzeren
Rilana | lady-3D |  |  | Minotaur afmaken |  | monitaur rig |  | bed
| Lady-U4 |  |  | Alchemist-3D |  | alchemsit rig |  | chair
|  |  |  | Alchemist-4U |  | lady rig |  | table
Alchemist-2D
Janneke | Huisjes textures |  |  | flowers |  | sprites en ui slab |  | pots
|  |  |  | animals |  |  | priority | pans
|  |  |  | nature pieces |  |  |  | candle
shields textures
Gerwin | Lvl Design[ |  |  | Temple maze Implementing
| Vegatation |  |  | Vegetation
Thomas | new in group |  |  | animation armen
Arne | new in group
Dees | new in group

## Sheet2
Assetlist
2D | Textures |  | 6A | Animaties |  | TXT | Textures | INT | Interactives
3D | Model |  | 7S | Sound |  | ENV | Environment | SPR | Sprites
4U | Unwrap |  | 8P | Particle |  | PRP | Prop
5R | Rigging |  | 9Sc | Script |  | Char | Character
Object |  | Code |  |  | Priority | Member
Characters
Minotaurus (Boss) |  | 2D-Char-Minotaurus |  |  | A | Rilana
|  | 3D-Char-Minotaurus |  |  | A | Rilana
|  | 4U-Char-Minotaurus |  |  | A | Rilana
|  | 5R-Char-Minotaurus |  |  | A | Rilana
Theseus |  | 2D-Char-Theseus |  |  | A | Rilana
|  | 3D-Char-Theseus |  |  | A | Rilana
|  | 4U-Char-Thesues |  |  | A | Rilana
|  | 5R-Char-Theseus |  |  | A | Rilana
Lady |  | 2D-Char-Lady |  |  | A | Maaike
|  | 3D-Char-Lady |  |  | A | Maaike
|  | 4U-Char-Lady |  |  | A | Maaike
|  | 5R-Char-Lady |  |  | A | Maaike
Villager 1 (old man) |  | 2D-Char-Villager1 |  |  | B
|  | 3D-Char-Villager1 |  |  | B
|  | 4U-Char-Villager1 |  |  | B
|  | 5R-Char-Villager1 |  |  | B
Villager 2 |  | 2D-Char-Villager2 |  |  | B
|  | 3D-Char-Villager2 |  |  | B
|  | 4D-Char-Villager2 |  |  | B
|  | 5R-Char-Villager2 |  |  | B
Environment
Houses
DoorWall |  | 2D-ENV-Doorwall |  |  | A
|  | 3D-ENV-Doorwall |  |  | A
|  | 4U-ENV-Doorwall |  |  | A
Window wall |  | 2D-ENV-Winwall |  |  | A
|  | 3D-ENV-Winwall |  |  | A
|  | 4U-ENV-Winwall |  |  | A
Wall |  | 2D-ENV-Wall |  |  | A
|  | 3D-ENV-Wall |  |  | A
|  | 4U-ENV-Wall |  |  | A
Window wall 2 |  | 2D-ENV-Winwall2 |  |  | B
|  | 3D-ENV-Winwall2 |  |  | B
|  | 4U-ENV-Winwall2 |  |  | B
Stair piece |  | 2D-ENV-Stair |  |  | A
|  | 3D-ENV-Stair |  |  | A
|  | 4U-ENV-Stair |  |  | A
Floor piece |  | 2D-ENV-Floor |  |  | A
|  | 3D-ENV-Floor |  |  | A
|  | 4U-ENV-Floor |  |  | A
Roof piece 1 |  | 2D-ENV-Roof1 |  |  | A
|  | 3D-ENV-Roof1 |  |  | A
|  | 4U-ENV-Roof1 |  |  | A
Roof piece 2 |  | 2D-ENV-Roof2 |  |  | B
|  | 3D-ENV-Roof2 |  |  | B
|  | 4U-ENV-Roof2 |  |  | B
Roof Terrace |  | 2D-ENV-RoofTer |  |  | A
|  | 3D-ENV-RoofTer |  |  | A
|  | 4U-ENV-RoofTer |  |  | A
Wall Edge |  | 2D-ENV-WallEdge |  |  | A
|  | 3D-ENV-WallEdge |  |  | A
|  | 4U-ENV-WallEdge |  |  | A
Temple
Piller |  | 2D-ENV-TemplePiller |  |  | A
|  | 3D-ENV-TemplePiller |  |  | A
|  | 4U-ENV-TemplePiller |  |  | A
Door |  | 2D-ENV-TempleDoor |  |  | A
|  | 3D-ENV-TempleDoor |  |  | A
|  | 4U-ENV-TempleDoor |  |  | A
Wall |  | 2D-ENV-TempleDoor |  |  | A
|  | 3D-ENV-TempleDoor |  |  | A
|  | 4U-ENV-TempleDoor |  |  | A
Roof |  | 2D-ENV-TempleRoof |  |  | A
|  | 3D-ENV-TempleRoof |  |  | A
|  | 4U-ENV-TempleRoof |  |  | A
Floor |  | 2D-ENV-TempleFloor |  |  | A
|  | 3D-ENV-TempleFloor |  |  | A
|  | 4U-ENV-TempleFloor |  |  | A
Stairs |  | 2D-ENV-TempleStair |  |  | A
|  | 3D-ENV-TempleStair |  |  | A
|  | 4U-ENV-TempleStair |  |  | A
Labyrinth piece 1 |  | 2D-ENV-Labyrinth1 |  |  | A
|  | 3D-ENV-Labyrinth1 |  |  | A
|  | 4U-ENV-Labyrinth1 |  |  | A
Labyrinth piece 2 |  | 2D-ENV-Labyrinth2 |  |  | B
|  | 3D-ENV-Labyrinth2 |  |  | B
|  | 4U-ENV-Labyrinth2 |  |  | B
Labyrinth circle |  | 2D-ENV-LabyCircle |  |  | A
|  | 3D-ENV-LabyCircle |  |  | A
|  | 4U-ENV-LabyCircle |  |  | A
Labyrinth piller |  | 2D-ENV-LabyPiller |  |  | A
|  | 3D-ENV-LabyPiller |  |  | A
|  | 4U-ENV-LabyPiller |  |  | A
Nature
Flower 1 |  | 2D-ENV-Flower1 |  |  | A
|  | 3D-ENV-Flower1 |  |  | A
|  | 4U-ENV-Flower1 |  |  | A
Flower 2 |  | 2D-ENV-Flower2 |  |  | B
|  | 3D-ENV-Flower2 |  |  | B
|  | 4U-ENV-Flower2 |  |  | B
Flower 3 |  | 2D-ENV-Flower3 |  |  | B
|  | 3D-ENV-Flower3 |  |  | B
|  | 4U-ENV-Flower3 |  |  | B
Tree 1 |  | 2D-ENV-Tree1 |  |  | A
|  | 3D-ENV-Tree1 |  |  | A
|  | 4U-ENV-Tree1 |  |  | A
Tree 2 |  | 2D-ENV-Tree2 |  |  | B
|  | 3D-ENV-Tree2 |  |  | B
|  | 4U-ENV-Tree2 |  |  | B
Mushroom 1 |  | 2D-ENV-Mushroom1 |  |  | A
|  | 3D-ENV-Mushroom1 |  |  | A
|  | 4U-ENV-Mushroom1 |  |  | A
Mushroom 2 |  | 2D-ENV-Mushroom2 |  |  | B
|  | 3D-ENV-Mushroom2 |  |  | B
|  | 4U-ENV-Mushroom2 |  |  | B
Bush 1 |  | 2D-ENV-Bush1 |  |  | A
|  | 3D-ENV-Bush1 |  |  | A
|  | 4U-ENV-Bush1 |  |  | A
Bush 2 |  | 2D-ENV-Bush2 |  |  | B
|  | 3D-ENV-Bush2 |  |  | B
|  | 4U-ENV-Bush2 |  |  | B
Bunny |  | 2D-ENV-Bunny |  |  | A
|  | 3D-ENV-Bunny |  |  | A
|  | 4U-ENV-Bunny |  |  | A
|  | 5R-ENV-Bunny |  |  | A
Rocks |  | 2D-ENV-Rocks |  |  | A
|  | 3D-ENV-Rocks |  |  | A
|  | 4U-ENV-Rocks |  |  | A
Treetrunks |  | 2D-ENV-Treetrunks |  |  | A
|  | 3D-ENV-Treetrunks |  |  | A
|  | 4U-ENV-Treetrunks |  |  | A
Props
Items
Sword |  | 2D-PRP-Sword |  |  | A | Janneke
|  | 3D-PRP-Sword |  |  | A | Janneke
|  | 4U-PRP-Sword |  |  | A | Janneke
Axe |  | 2D-PRP-Axe |  |  | A | Rilana
|  | 3D-PRP-Axe |  |  | A | Rilana
|  | 4U-PRP-Axe |  |  | A | Rilana
Torch |  | 2D-PRP-Torch |  |  | A
|  | 3D-PRP-Torch |  |  | A
|  | 4U-PRP-Torch |  |  | A
Props
Flower Box |  | 2D-PRP-Flowerbox |  |  | A
|  | 3D-PRP-Flowerbox |  |  | A
|  | 4U-PRP-Flowerbox |  |  | A
Chair |  | 2D-PRP-Chair |  |  | A
|  | 3D-PRP-Chair |  |  | A
|  | 4U-PRP-Chair |  |  | A
Table |  | 2D-PRP-Table |  |  | A
|  | 3D-PRP-Table |  |  | A
|  | 4U-PRP-Table |  |  | A
Candle |  | 2D-PRP-Candle |  |  | A
|  | 3D-PRP-Candle |  |  | A
|  | 4U-PRP-Candle |  |  | A
Pillars |  | 2D-PRP-Pillars |  |  | A
|  | 3D-PRP-Pillars |  |  | A
|  | 4U-PRP-Pillars |  |  | A
Well |  | 2D-PRP-Well |  |  | A
|  | 3D-PRP-Well |  |  | A
|  | 4U-PRP-Well |  |  | A
Chest |  | 2D-PRP-Chest |  |  | A
|  | 3D-PRP-Chest |  |  | A
|  | 4U-PRP-Chest |  |  | A
Bones |  | 2D-PRP-Bones |  |  | A
|  | 3D-PRP-Bones |  |  | A
|  | 4U-PRP-Bones |  |  | A
Shields |  | 2D-PRP-Shields |  |  | A
|  | 3D-PRP-Shields |  |  | A
|  | 4U-PRP-Shields |  |  | A
Jars |  | 2D-PRP-Jars |  |  | A
|  | 3D-PRP-Jars |  |  | A
|  | 4U-PRP-Jars |  |  | A
Hanging Torch |  | 2D-PRP-HangTorch |  |  | A
|  | 3D-PRP-HangTorch |  |  | A
|  | 4U-PRP-HangTorch |  |  | A
Coins |  | 2D-PRP-Coins |  |  | B
|  | 3D-PRP-Coins |  |  | B
|  | 4U-PRP-Coins |  |  | B
Scrolls |  | 2D-PRP-Scroll |  |  | B
|  | 3D-PRP-Scroll |  |  | B
|  | 4U-PRP-Scroll |  |  | B
Bed |  | 2D-PRP-Bed |  |  | A
|  | 3D-PRP-Bed |  |  | A
|  | 4U-PRP-Bed |  |  | A
Pots |  | 2D-PRP-Pots |  |  | A
|  | 3D-PRP-Pots |  |  | A
|  | 4U-PRP-Pots |  |  | A
couch |  | 2D-PRP-Couch |  |  | A
|  | 3D-PRP-Couch |  |  | A
|  | 4U-PRP-Couch |  |  | A
Code
CraftingStation |  | 9Sc-CraftingStation |  |  | A
GameManager |  | 9Sc-GameManager |  |  | A
Minotaur |  | 9Sc-Minotaur |  |  | A
Npc |  | 9Sc-Npc |  |  | A
DialogueManager |  | 9Sc-DialogueManager |  |  | A
InventoryManager |  | 9Sc-InventoryManager |  |  | A
Item |  | 9Sc-Item |  |  | A
FpsInputController |  | 9sc-FpsInputController |  |  | A
CombatManager |  | 9sc-CombatManager |  |  | A
UIManager |  | 9Sc-UIManager |  |  | A
Particle/Sprite
Grass |  | 2D-ENV-Grass |  |  | A
Cloud |  | 8P-ENV-Cloud |  |  | A
Waterfall |  | 8P-eNV-Waterfall |  |  | A
tempel
building
props
axe
tablet